## Sheet1
Risk ID | Risk Description | Probability | Impact | Mitigation
R-01 | System downtime during registration | Medium | High | Cloud hosting and backups
R-02 | Unauthorized access | Medium | High | Role-based access control
R-03 | High user load during peak periods | High | High | Performance testing
R-04 | Data loss | Low | High | Daily backups
R-05 | Requirement changes | Medium | Medium | Regular stakeholder reviews
R-06 | Project delays | Medium | Medium | Weekly progress tracking